## Master Project Plan
Acquisition Transition Task List
The Beckemeier Law Firm
Task | Transition Category | Responsibility | Due Date | Status | Date Completed | Notes
Ownership Agreement | Business Transition
Determine new entity structure | Business Transition
New operating agreement(s) | Business Transition
New entity created with State | Business Transition
New entity created Federally (FEIN) | Business Transition
New Bank accounts opened if needed | Business Transition
New entity names (if multiple) | Brand Transition
Determine new firm name for branding purposes | Brand Transition
New brand and logo strategy | Brand Transition
Complete list of clients with contact info | Client Transition
Draft and finalize Letters to Clients | Client Transition
Notify clients by phone (for certain clients) from Attorneys and then email about the transition with letter and new documents to sign. | Client Transition
Send letters out by email to clients | Client Transition
Fee agreements/engagement letters sent to clients after affirmation of whether they are staying with current firm or going to new firm | Business Transition
Create new website with new brand | Brand Transition
Obtain technology for new partner (computer, phone etc…) | Business Transition
Set-up office for new partners | Business Transition
Set up benefit plans for new Firm (health, dental, IRA/401(k)) | Business Transition
Malpractice Insurance modifications | Business Transition
Set-up new lawyers and staff in Clio billing software | Business Transition
Connect banks and new credit cards if applicable to firm QBO/Accounting Software | Business Transition
Office 365 and othere software licenes | Business Transition
Transfer digital matters in case management system from one account to the other once client's have signed new documents | Client Transition
Start on a marketing plan for announcement of new brand/firm | Brand Transition
Track letters received and remind clients who have not yet signed. | Client Transition
Budget modifications | Business Transition
Letterhead | Brand Transition
Email Signature for all employees with new brand | Brand Transition
Transfer of A/R digitally (should go with matter transfer in system) OR Close out old A/R and set up working cap. Loan from BLF to new Firm | Business Transition
Physical/digital matter documenation logistics (organizing documentation to go to each new entity) | Client Transition
New photos of partner and other lawyers | Brand Transition
Set up payroll for new Firm and partner LLCs | Business Transition
Strategic Plan alterations | Business Transition
Notify courts for substitution of counsel | Client Transition
Create email address for new brand and/or employees | Business Transition
Determine Bill rates | Business Transition
Domain options for new firm | Brand Transition
Payroll set-up in new entity | Business Transition
New software licenses: Billing program Internal Programs, Document Management etc… | Business Transition
Migrate date from old to new system if applicable | Business Transition
Close old software programs or remove/lessen licenses | Business Transition
Replace all online profiles for Attorney registry listings with new entity (FindLaw, Avvo, Superlawyers, Martindale etc…) | Brand Transition
Create new engagement letters for new firm name | Client Transition